## Overview
Project Name |  |  | Archivist
Current Project Week |  |  | 1
Project Type | PRO-1 |  | 3 |  | ECTS
Project Life Span |  |  | 12 |  | Weeks
Resulting Workload |  |  | 4500 |  | Minutes
|  |  | 75 |  | Hours
|  |  | ca. | 6.25 | Hours per week
Current Overview | [5 empty] | Complete Overview
Week Nr. |  | 1 | Debit Hours (as planned) | Actual Hours | Difference | Week Overview | 17.04 - 23.04.2017 | 24.04 - 30.04.2017 | 01.05 - 07.05.2017 | 08.05 - 14.05.2017 | 15.05 - 21.05.2017 | 22.05 - 28.05.2017 | 29.05 - 04.06.2017 | 05.06 - 11.06.2017 | 12.06 - 18.06.2017 | 19.06 - 25.06.2017 | 26.06 - 02.07.2017 | 03.07 - 09.07.2017 | DD.MM - DD.MM.YYYY | DD.MM - DD.MM.YYYY | DD.MM - DD.MM.YYYY | DD.MM - DD.MM.YYYY | DD.MM - DD.MM.YYYY | DD.MM - DD.MM.YYYY | DD.MM - DD.MM.YYYY | DD.MM - DD.MM.YYYY | Sum | Debit Hours - Complete - | Difference - Complete -
[7 empty] | Week 01 | Week 02 | Week 03 | Week 04 | Week 05 | Week 06 | Week 07 | Week 08 | Week 09 | Week 10 | Week 11 | Week 12 | R-Week 13 | R-Week 14 | R-Week 15 | R-Week 16 | R-Week 17 | R-Week 18 | R-Week 19 | R-Week 20
Boris Fuchs |  |  | 0 | 4 | 4 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | -67
[6 empty] | Actual | 4 | 0 | 0 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
[6 empty] | Difference | 4 | 0 | 0 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
Paul Schmutz |  |  | 0 | 4 | 4 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | -58
[6 empty] | Actual | 4 | 0 | 0 | 3 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17
[6 empty] | Difference | 4 | 0 | 0 | 3 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17
---- |  |  | 0 | 0 | 0 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Difference | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
---- |  |  | 0 | 0 | 0 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Difference | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
---- |  |  | 0 | 0 | 0 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Difference | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Std-A
Time Recording
Boris Fuchs
Week 01 |  |  |  | 17.04 - 23.04.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 | Grundlegende Strukturierung | 210 | Minutes | Grundlegende Strukturierung und Planung des Projekts; Brainstorming, Zieldefinition
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 4 | Hours
Geplant |  | 0 | Hours
Week 02 |  |  |  | 24.04 - 30.04.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 03 |  |  |  | 01.05 - 07.05.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 04 |  |  |  | 08.05 - 14.05.2017
Nr | Type of Work | Duration |  | Comment
1 | psp Erstellung | 60 | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 1 | Hours
Geplant |  | 0 | Hours
Week 05 |  |  |  | 15.05 - 21.05.2017
Nr | Type of Work | Duration |  | Comment
1 | Pflichtenheft | 90 | Minutes | Punkt 1 & 2
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 2 | Hours
Geplant |  | 0 | Hours
Week 06 |  |  |  | 22.05 - 28.05.2017
Nr | Type of Work | Duration |  | Comment
1 | Pflichtenheft | 60 | Minutes | Zusammenführen, diskutieren
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 1 | Hours
Geplant |  | 0 | Hours
Week 07 |  |  |  | 29.05 - 04.06.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 08 |  |  |  | 05.06 - 11.06.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 09 |  |  |  | 12.06 - 18.06.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 10 |  |  |  | 19.06 - 25.06.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week11 |  |  |  | 26.06 - 02.07.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 12 |  |  |  | 03.07 - 09.07.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 13 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 14 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 15 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 16 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 17 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 18 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 19 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 20 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours

## Std-B
Time Recording
Paul Schmutz
Week 01 |  |  |  | 17.04 - 23.04.2017
Nr | Type of Work | Duration |  | Comment
1 | Grundlegende Strukturierung | 210 | Minutes | Grundlegende Strukturierung und Planung des Projekts; Brainstorming, Zieldefinition
2 | Meeting mit Musikverein | 30 | Minutes | Befragung Kapellmeister & Archivarin der TMK Wallsee-Sindelburg über Funktionsumfang
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 4 | Hours
Geplant |  | 0 | Hours
Week 02 |  |  |  | 24.04 - 30.04.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 03 |  |  |  | 01.05 - 07.05.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 04 |  |  |  | 08.05 - 14.05.2017
Nr | Type of Work | Duration |  | Comment
1 | psp Erstellung | 60 | Minutes
2 | Mockups | 90 | Minutes | Beginnen mit Mockups Design in Adobe XD
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 3 | Hours
Geplant |  | 0 | Hours
Week 05 |  |  |  | 15.05 - 21.05.2017
Nr | Type of Work | Duration |  | Comment
1 | Pflichtenheft | 30 | Minutes | Punkt 4.1, Dokument-Design
2 | Mockups | 50 | Minutes | Titelübersicht Design
3 | Mockups | 50 | Minutes | Titelübersicht Design, Musikstück Design
4 | Pflichtenheft | 150 | Minutes | Punkt 4, project environment
5 | Mockups, PSP | 60 | Minutes | Mockups 1. volle Version fertig, PSP aktualisieren (Backend + Frontend Tasks)
6 |  |  | Minutes
Sum |  | 6 | Hours
Geplant |  | 0 | Hours
Week 06 |  |  |  | 22.05 - 28.05.2017
Nr | Type of Work | Duration |  | Comment
1 | Pflichtenheft | 60 | Minutes | Zusammenführen, diskutieren
2 | Pflichtenheft | 60 | Minutes | Anpassungen lt. Besprechung
3 | Pflichtenheft, Mockups | 100 | Minutes | Anpassungen lt. Besprechung
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 4 | Hours
Geplant |  | 0 | Hours
Week 07 |  |  |  | 29.05 - 04.06.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 08 |  |  |  | 05.06 - 11.06.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 09 |  |  |  | 12.06 - 18.06.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 10 |  |  |  | 19.06 - 25.06.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 11 |  |  |  | 26.06 - 02.07.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 12 |  |  |  | 03.07 - 09.07.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 13 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 14 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 15 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 16 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 17 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 18 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 19 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 20 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours

## Std-C
Time Recording
----
Week 01 |  |  |  | 17.04 - 23.04.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 02 |  |  |  | 24.04 - 30.04.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 03 |  |  |  | 01.05 - 07.05.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 04 |  |  |  | 08.05 - 14.05.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 05 |  |  |  | 15.05 - 21.05.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 06 |  |  |  | 22.05 - 28.05.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 07 |  |  |  | 29.05 - 04.06.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 08 |  |  |  | 05.06 - 11.06.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 09 |  |  |  | 12.06 - 18.06.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 10 |  |  |  | 19.06 - 25.06.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 11 |  |  |  | 26.06 - 02.07.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 12 |  |  |  | 03.07 - 09.07.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 13 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 14 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 15 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 16 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 17 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 18 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 19 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 20 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours

## Std-D
Time Recording
----
Week 01 |  |  |  | 17.04 - 23.04.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 02 |  |  |  | 24.04 - 30.04.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 03 |  |  |  | 01.05 - 07.05.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 04 |  |  |  | 08.05 - 14.05.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 05 |  |  |  | 15.05 - 21.05.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 06 |  |  |  | 22.05 - 28.05.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 07 |  |  |  | 29.05 - 04.06.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 08 |  |  |  | 05.06 - 11.06.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 09 |  |  |  | 12.06 - 18.06.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 10 |  |  |  | 19.06 - 25.06.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 11 |  |  |  | 26.06 - 02.07.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 12 |  |  |  | 03.07 - 09.07.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 13 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 14 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 15 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 16 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 17 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 18 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 19 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 20 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours

## Std-E
Time Recording
----
Week 01 |  |  |  | 17.04 - 23.04.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 02 |  |  |  | 24.04 - 30.04.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 03 |  |  |  | 01.05 - 07.05.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 04 |  |  |  | 08.05 - 14.05.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 05 |  |  |  | 15.05 - 21.05.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 06 |  |  |  | 22.05 - 28.05.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 07 |  |  |  | 29.05 - 04.06.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 08 |  |  |  | 05.06 - 11.06.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 09 |  |  |  | 12.06 - 18.06.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 10 |  |  |  | 19.06 - 25.06.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 11 |  |  |  | 26.06 - 02.07.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 12 |  |  |  | 03.07 - 09.07.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 13 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 14 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 15 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 16 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 17 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 18 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 19 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 20 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours

## dynamic Data
Project Weeks
Week 1 | 17.04 - 23.04.2017
Week 2 | 24.04 - 30.04.2017
Week 3 | 01.05 - 07.05.2017
Week 4 | 08.05 - 14.05.2017
Week 5 | 15.05 - 21.05.2017
Week 6 | 22.05 - 28.05.2017
Week 7 | 29.05 - 04.06.2017
Week 8 | 05.06 - 11.06.2017
Week 9 | 12.06 - 18.06.2017
Week 10 | 19.06 - 25.06.2017
Week 11 | 26.06 - 02.07.2017
Week 12 | 03.07 - 09.07.2017
R-Week 13 | DD.MM - DD.MM.YYYY
R-Week 14 | DD.MM - DD.MM.YYYY
R-Week 15 | DD.MM - DD.MM.YYYY
R-Week 16 | DD.MM - DD.MM.YYYY
R-Week 17 | DD.MM - DD.MM.YYYY
R-Week 18 | DD.MM - DD.MM.YYYY
R-Week 19 | DD.MM - DD.MM.YYYY
R-Week 20 | DD.MM - DD.MM.YYYY
Participantes
Std-A | Boris Fuchs
Std-B | Paul Schmutz
Std-C | ----
Std-D | ----
Std-E | ----
Project Types
PRO-1
PRO-2
PRO-3
PRO-4
PRO-2-M
PRO-3-M